## Sheet1
User Stories	Task	Priority	Story Point
Project Initialization	Initialize NextJS FrontEnd Project	P0	5 SP
	Initialize Springboot BackEnd Project	P0	5 SP
	Create Database Structure	P0	3 SP
	Connect BE to Database	P0	2 SP
	Create CORS Configuration for BE	P0	2 SP
User can upload and download image	[BE] Create image download API	P0	3 SP
	[BE] Create image upload API	P0	3 SP
User can manage account	[BE] Create register API	P0	3 SP
	[BE] Create user info API	P0	3 SP
	[BE] Create user update API	P1	3 SP
	[BE] Create merchant apply API	P1	3 SP
	[FE] Create register page	P0	3 SP
	[FE] Create home page	P0	5 SP
	[FE] Create User Info page	P1	3 SP
	[FE] Create User update page	P1	5 SP
	[FE] Create apply to merchant button	P1	1 SP
User can manage session	[FE] Create login page	P0	4 SP
	[FE] Create logout button	P0	2 SP
	[BE] Create login API	P0	3 SP
	[BE] Create logout API	P0	3 SP
User can browse item and / Get recommendation base on their activities	[BE] Create item query list API	P0	3 SP
	[BE] Create item filter API	P0	3 SP
	[BE] Create item info API	P0	3 SP
	[BE] Create new table for knowledge graph calculation	P0	2 SP
	[BE] Create GetRecommendation API	P0	5 SP
	[FE] Add recommendation widget in homepage	P0	3 SP
	[FE] Create search page	P0	5 SP
	[FE] Create item detail page	P0	3 SP
User can discuss with other user and merchant	[BE] Create discussion create API	P2	3 SP
	[BE] Create edit discussion API	P2	3 SP
	[BE] Create delete discussion API	P2	3 SP
	[FE] Add widget for discussion in item detail page	P2	2 SP
User can manage wishlist	[BE] Create add to wishlist API	P1	2 SP
	[BE] Create remove from wishlist API	P1	2 SP
	[BE] Create query wishlist API	P1	3 SP
	[FE] Create add to wishlist button in / Item widget and item detail page	P1	1 SP
	[FE] Create wishlist page	P1	3 SP
User can manage cart	[BE] Create add to cart API	P0	2 SP
	[BE] Create update cart API	P0	2 SP
	[BE] Create query cart API	P0	2 SP
	[FE] Create add to cart button in item detail page	P1	1 SP
	[FE] Create cart page	P1	3 SP
User can do transaction	[BE] Integrate with midtrans for payment	P0	2 SP
	[BE] Create Transaction Create API	P1	2 SP
	[BE] Create Transaction Cancel API	P1	1 SP
	[BE] Create Transaction Finish API	P1	1 SP
	[BE] Create Transaction Query API	P1	2 SP
	[FE] Create Transaction list page	P1	2 SP
	[FE] Create Transaction pay page	P1	2 SP
	[FE] Create Transaction detail page	P1	2 SP
	[FE] Add “Pay” Button in cart page	P1	1 SP
User can create review and view existing review	[BE] Create API for creating review	P2	2 SP
	[BE] Create API for query review	P2	2 SP
	[FE] Create page for create review	P2	3 SP
	[FE] Create page for merchant review	P2	2 SP
	[FE] Create page for existing user review	P2	2 SP
Merchant can their items	[BE] Create API for create new item	P1	3 SP
	[BE] Create API for update item information	P1	3 SP
	[BE] Create API for delete item	P1	3 SP
	[FE] Create page for create item	P1	3 SP
	[FE] Create page for update item	P1	3 SP
	[FE] Create button for create item in merchant page	P2	1 SP
	[FE] Create button for edit item in item detail page	P2	1 SP
	[FE] Create button for delete item in item detail page	P2	1 SP